## Compzit -Redesign - Schedule
Compzit (Redesign & Development)
Module | Page | Desgn Status | Designer Review Status | Client Review Status | Redesign Status | Final Review Status | Development Status | Testing Status
App Administration | add_business_unit | Completed | Completed | Completed | Completed | Completed | From 25 may to 29 may 2020
App Administration | add_bank | Completed | Completed | Completed | Completed | Completed
App Administration | bank | Completed | Completed(Add print icon, search print should match finance account group, search textbox should be in bottom) | Completed | Completed | Completed
App Administration | business_unit | Completed | Completed(Add print icon, search print should match finance account group, search textbox should be in bottom)
App Administration | edit_organization | Completed
App Administration | add_premise | Completed
App Administration | add_premise_area | Completed
App Administration | add_corp_department | Completed
App Administration | add_city | Completed
App Administration | add_state | Completed
App Administration | add_time_slot | Completed
App Administration | add_complaint | Completed
App Administration | add_insurance | Completed
App Administration | insurance | Completed
App Administration | edit_password | Completed
App Administration | password | Completed
App Administration | add_corp_division | Completed
App Administration | add_workstation | Completed
App Administration | premise_area | Completed
App Administration | premise | Completed
App Administration | add_corp_partner | Completed
App Administration | add_country | Completed
App Administration | corp_division | Completed
App Administration | city | Completed
App Administration | corp_partner | Completed
App Administration | corp_department | Completed
App Administration | complaint | Completed
App Administration | workstation | Completed
App Administration | time_slot | Completed
App Administration | country | Completed
App Administration | state | Completed
Auto Workshop Management System | add_leave_typ | Completed
Auto Workshop Management System | add_trafic_viola_settlemnt | Completed
Auto Workshop Management System | add_water_card | Completed
Auto Workshop Management System | add_water_card_rechrg | Completed
Auto Workshop Management System | add_vehicle | Completed
Auto Workshop Management System | add_job | Completed
Auto Workshop Management System | add_holiday_deatls | Completed
Auto Workshop Management System | add_traffic_violation | Completed
Auto Workshop Management System | water_card_rechrg | Completed
Auto Workshop Management System | water_card | Completed
Auto Workshop Management System | water_billing | Completed
Auto Workshop Management System | vehicle_sts_mstr | Completed
Auto Workshop Management System | vehicle_renwl_lst | Completed
Auto Workshop Management System | vehicle_lst | Completed
Auto Workshop Management System | vehicle_cls | Completed
Auto Workshop Management System | vehicle_altmnt | Completed
Auto Workshop Management System | trafic_violation | Completed
Auto Workshop Management System | trafic_viola_settlemnt | Completed
Auto Workshop Management System | time_sheet_rprt | Completed
Auto Workshop Management System | leave_typ | Completed
Auto Workshop Management System | job_schedule | Completed
Auto Workshop Management System | insrnce_typ | Completed
Auto Workshop Management System | holiday | Completed
Auto Workshop Management System | fuel_typ | Completed
Auto Workshop Management System | emply_off_duty | Completed
Auto Workshop Management System | duty_roster_rprt | Completed
Auto Workshop Management System | duty_roster | Completed
Auto Workshop Management System | add_water_billing | Completed
Auto Workshop Management System | add_vhcl_insre_renwl | Completed
Auto Workshop Management System | add_vehicle_sts_mstr | Completed
Auto Workshop Management System | add_vehicle_cls | Completed
Auto Workshop Management System | add_vehicle_asgn | Completed
Auto Workshop Management System | add_job_schedule | Completed
Auto Workshop Management System | add_insrnce_typ | Completed
Auto Workshop Management System | add_fuel_typ | Completed
Auto Workshop Management System | job | Completed
Gurantee Management System | policy | Completed
Gurantee Management System | prjct_wse_grnty_rpt | Completed
Gurantee Management System | notfiction_tmplte | Completed
Gurantee Management System | supplr_rpt_wys | Completed
Gurantee Management System | supplr_rpt_opn_status | Completed
Gurantee Management System | supplr_rpt_expry_3mnth | Completed
Gurantee Management System | rqst_4_guarant | Completed
Gurantee Management System | supplr_rpt_crntly_rning | Completed
Gurantee Management System | mail_trckng_rpt | Completed
Gurantee Management System | job_catgry | Completed
Gurantee Management System | insrnce_rpt_projct_wys | Completed
Gurantee Management System | insrnce_rpt_typ_bsd | Completed
Gurantee Management System | insrnce_rpt_opn_status | Completed
Gurantee Management System | insrnce_rpt_expired | Completed
Gurantee Management System | insrnce_rpt_expry_rnge | Completed
Gurantee Management System | insrnce_rpt_expry_3mnth | Completed
Gurantee Management System | cntrct | Completed
Gurantee Management System | custmr_rpt_crntly_rning | Completed
Gurantee Management System | custmr_rpt_expired | Completed
Gurantee Management System | custmr_rpt_expry_3mnth | Completed
Gurantee Management System | custmr_rpt_grnty | Completed
Gurantee Management System | custmr_rpt_opn_status | Completed
Gurantee Management System | grnty_expry_rng_rpt | Completed
Gurantee Management System | grnty_mod_wis_rpt | Completed
Gurantee Management System | guarnty_catgry | Completed
Gurantee Management System | add_rqst_4_guarant | Completed
Gurantee Management System | add_cntrct | Completed
Gurantee Management System | add_guarnty_catgry | Completed
Gurantee Management System | add_policy | Completed
Gurantee Management System | add_notfiction_tmplte | Completed
Gurantee Management System | add_job_catgry | Completed
Gurantee Management System | add_cntrct_catgry | Completed
Gurantee Management System | insrnce_typ | Completed
Gurantee Management System | insrnce_rpt_crntly_rning | Completed
Gurantee Management System | add_insrnce_typ | Completed
Gurantee Management System | cntrct_catgry | Completed
Gurantee Management System | exprd_bnk_grnty_rpt | Completed
Human Capital Management | attendace_report | Completed
Human Capital Management | add_emply_job_assign | Completed
Human Capital Management | emply_page_new | Completed
Human Capital Management | rpt_emply_adtn_dedctn | Completed
Human Capital Management | mntly_slry_stmnt | Completed
Human Capital Management | leave_aplction_sts_rtp | Completed
Human Capital Management | add_leave_aplction_sts_rtp | Completed
Human Capital Management | app_settings | Completed
Human Capital Management | bulk_labr | Completed
Human Capital Management | graph_test | Completed
Human Capital Management | immigrtion_asgnmt | Completed
Human Capital Management | add_immigrtion_round | Completed
Human Capital Management | immigrtion_rounds | Completed
Human Capital Management | joining_intmtion_edit | Completed
Human Capital Management | joining_intmtion | Completed
Human Capital Management | interview_process_edit | Completed
Human Capital Management | intrvw_procss | Completed
Human Capital Management | intrvw_panel_edit | Completed
Human Capital Management | appointmnt_lttr | Completed
Human Capital Management | add_appointmnt_lttr | Completed
Human Capital Management | shrtlist_cndidate_edit | Completed
Human Capital Management | add_candidte_selection | Completed
Human Capital Management | candidat_selctn | Completed
Human Capital Management | add_interview_cat | Completed
Human Capital Management | require_allocation | Completed
Human Capital Management | job_notification | Completed
Human Capital Management | job_notification_click | Completed
Human Capital Management | slry_entry_process | Completed
Human Capital Management | payroll_strctr | Completed
Human Capital Management | add_job_descrptn | Completed
Human Capital Management | job_role | Completed
Human Capital Management | add_employee | Completed
Human Capital Management | add_manpwr_reqmnt | Completed
Human Capital Management | manpowr_reqrmnt | Completed
Human Capital Management | add_license_type | Completed
Human Capital Management | add_acco_type | Completed
Human Capital Management | accomodation_type | Completed
Human Capital Management | add_eply_role_aloction | Completed
Human Capital Management | add_designation | Completed
Human Capital Management | designation_mstr | Completed
Human Capital Management | emply_attendnce_port | Completed
Human Capital Management | add_emply_bulk | Completed
Human Capital Management | add_emply_single | Completed
Human Capital Management | employee_transfer | Completed
Human Capital Management | add_indvdual_leave_typ | Completed
Human Capital Management | end_of_srvce_settlmnt | Completed
Human Capital Management | emply_rol_allow | Completed
Human Capital Management | emply_registratn | Completed
Human Capital Management | emply_mess_exceptn | Completed
Human Capital Management | emply_deductn | Completed
Human Capital Management | emply_cndct_incidnt | Completed
Human Capital Management | employee_condct | Completed
Human Capital Management | emp_dtl_rpt | Completed
Human Capital Management | daily_attendance | Completed
Human Capital Management | duty_rejoin | Completed
Human Capital Management | consultancy | Completed
Human Capital Management | add_certificate_bundle | Completed
Human Capital Management | arrival_confrmtion | Completed
Human Capital Management | add_worker | Completed
Human Capital Management | add_staff | Completed
Human Capital Management | add_job_role | Completed
Human Capital Management | add_performance_template | Completed
Human Capital Management | add_performance_form | Completed
Human Capital Management | add_pay_grade | Completed
Human Capital Management | add_notice_period | Completed
Human Capital Management | add_leave_type | Completed
Human Capital Management | add_exprnce_crtfcte_gen | Completed
Human Capital Management | add_consltncy | Completed
Human Capital Management | add_accommodation | Completed
Human Capital Management | accomodation | Completed
Human Capital Management | welfare_service_transction | Completed
Human Capital Management | add_welfare_service_transaction | Completed
Human Capital Management | add_welfare_service_category | Completed
Human Capital Management | welfare_service_category | Completed
Human Capital Management | add_welfare_service | Completed
Human Capital Management | welfare_service | Completed
Human Capital Management | add_visa_quota | Completed
Human Capital Management | visa_quota | Completed
Human Capital Management | add_team_hier | Completed
Human Capital Management | team_hier | Completed
Human Capital Management | add_salary_certificate | Completed
Human Capital Management | salary_certificate | Completed
Human Capital Management | leave_approval | Completed
Human Capital Management | ref_leave_approval | Completed
Human Capital Management | performance_templ | Completed
Human Capital Management | performance_form | Completed
Human Capital Management | add_paymnt_closng_process | Completed
Human Capital Management | payment_closing | Completed
Human Capital Management | pay_grade | Completed
Human Capital Management | add_overtime_category | Completed
Human Capital Management | overtime_category | Completed
Human Capital Management | notice_period | Completed
Human Capital Management | monthly_attendance | Completed
Human Capital Management | add_monthly_attendance | Completed
Human Capital Management | add_mess_bill | Completed
Human Capital Management | mess_bill_cal | Completed
Human Capital Management | licence_type | Completed
Human Capital Management | leave_type | Completed
Human Capital Management | add_leave_settlemnt | Completed
Human Capital Management | leave_settlement | Completed
Human Capital Management | add_leave_reqst | Completed
Human Capital Management | leave_request | Completed
Human Capital Management | add_leave_allocation | Completed
Human Capital Management | leave_allocation | Completed
Human Capital Management | joining_worker | Completed
Human Capital Management | job_descrptn | Completed
Human Capital Management | intrvw_templte | Completed
Human Capital Management | intrvw_panel | Completed
Human Capital Management | intrvw_catgry | Completed
Human Capital Management | generate_wps | Completed
Human Capital Management | add_generate_wps | Completed
Human Capital Management | add_exit_intrvw_qstn | Completed
Human Capital Management | ext_intrvw_question | Completed
Human Capital Management | exprnce_crtfcte_genrtion | Completed
Human Capital Management | exit_intrview_process_click | Completed
Human Capital Management | exit_intrvw_process | Completed
Human Capital Management | add_end_of_srvce_settlmnt | Completed
Human Capital Management | add_emplye_cndct_catgry | Completed
Human Capital Management | emplye_cndct_catgry | Completed
Human Capital Management | emply_sponsor | Completed
Human Capital Management | add_emply_sponsor | Completed
Human Capital Management | add_emply_mess_exceptn | Completed
Human Capital Management | add_emply_deductn | Completed
Human Capital Management | add_emply_cndct_incidnt | Completed
Human Capital Management | add_daily_attendance_sheet | Completed
Human Capital Management | add_clearance_form_worker | Completed
Human Capital Management | clearance_form_workr | Completed
Human Capital Management | add_certfcate_vlidtion | Completed
Human Capital Management | certfcate_vlidtion | Completed
Human Capital Management | certfcate_bundl_temp | Completed
Human Capital Management | candidat_short | Completed
Human Capital Management | add_adictn_dedctn_nrml | Completed
Human Capital Management | adictn_dedctn | Completed
Human Capital Management | add_monthly_salary_process | Completed
Human Capital Management | add_exit_process | Completed
Human Capital Management | add_adictn_dedctn | Completed
Human Capital Management | add_accomdtion_catgry | Completed
Human Capital Management | visa_profession | Completed
Human Capital Management | rpt_visa_quota_status | Completed
Human Capital Management | rpt_visa_bundle | Completed
Human Capital Management | rpt_payroll_process | Completed
Human Capital Management | rpt_onbrdng_job_asgnmnt | Completed
Human Capital Management | rpt_onboarding_status | Completed
Human Capital Management | rpt_mess_calculation | Completed
Human Capital Management | rpt_manpwr_prcess_dtl | Completed
Human Capital Management | rpt_manpwr_job_asgnment | Completed
Human Capital Management | rpt_man_powr_rqrmnt_sts | Completed
Human Capital Management | rpt_leave_mngmnt | Completed
Human Capital Management | rpt_leave_application | Completed
Human Capital Management | rpt_job_ofr_status | Completed
Human Capital Management | rpt_job_cst_smmry | Completed
Human Capital Management | rpt_intrvw_evaltion | Completed
Human Capital Management | rpt_intrview_summry | Completed
Human Capital Management | rpt_imigrtion_task | Completed
Human Capital Management | rpt_expry_notification | Completed
Human Capital Management | rpt_emply_recruit | Completed
Human Capital Management | rpt_emply_deduction_dtl | Completed
Human Capital Management | rpt_emp_dtl | Completed
Human Capital Management | rpt_attendance | Completed
Human Capital Management | rpt_accomodation | Completed
Human Capital Management | resignation_apprvl | Completed
Human Capital Management | resignation | Completed
Human Capital Management | performance_evaluation | Completed
Human Capital Management | payslip_generation | Completed
Human Capital Management | passport_hnd_ovr_sts | Completed
Human Capital Management | opening_leave_alloctn | Completed
Human Capital Management | onboardng_task | Completed
Human Capital Management | onboardng_procss | Completed
Human Capital Management | notice_period_alloction | Completed
Human Capital Management | mntly_slry_stmnt_wrkr | Completed
Human Capital Management | leave_partial | Completed
Human Capital Management | leave_facility_assgnmnt | Completed
Human Capital Management | joining_staff | Completed
Human Capital Management | job_delegation | Completed
Human Capital Management | import_csv | Completed
Human Capital Management | immigrtion_task | Completed
Human Capital Management | exit_procedure | Completed
Human Capital Management | exit_partl_process | Completed
Human Capital Management | emply_exit_process | Completed
Human Capital Management | clearance_form_apprvl | Completed
Human Capital Management | candidate_login_page | Completed
Human Capital Management | candidate_id_generate | Completed
Human Capital Management | accomdtion_catgry | Completed
Procurement Management Solution | prchse_ordr | Completed
Procurement Management Solution | add_purchase | Completed
Procurement Management Solution | ware_house | Completed
Procurement Management Solution | active_apprvl | Completed
Procurement Management Solution | add_apprvl_console | Completed
Procurement Management Solution | add_replace_apprvr | Completed
Procurement Management Solution | add_dcmnt_wrkflow | Completed
Procurement Management Solution | dcmt_work | Completed
Procurement Management Solution | add_apprvl_assmnt | Completed
Procurement Management Solution | apprvl_assmnt | Completed
Procurement Management Solution | approvl-set_list | Completed
Procurement Management Solution | add_apprvl_set | Completed
Procurement Management Solution | aprved_hie_tmp | Completed
Procurement Management Solution | add_aprved_hie_tmp | Completed
Procurement Management Solution | vendor | Completed
Procurement Management Solution | add_vendor | Completed
Procurement Management Solution | add_warehouse | Completed
Procurement Management Solution | approvl-set_dcmt | Completed
Procurement Management Solution | add_charge_heads | Completed
Procurement Management Solution | charge_heads | Completed
Sales Force Automation | product_master | Completed
Sales Force Automation | customer_master | Completed
Sales Force Automation | rpt_custom_se | Completed
Sales Force Automation | rpt_active_opp | Completed
Sales Force Automation | rpt_daily_se | Completed
Sales Force Automation | rpt_daily_dm | Completed
Sales Force Automation | rpt_custom_dm | Completed
Sales Force Automation | rpt_booking_se | Completed
Sales Force Automation | rpt_booking_dm | Completed
Sales Force Automation | rpt_opportunity | Completed
Sales Force Automation | ref_opportunity | Completed
Sales Force Automation | rpt_itemlist | Completed
Sales Force Automation | template | Completed
Sales Force Automation | standard_template | Completed
Sales Force Automation | project_template | Completed
Sales Force Automation | rpt_qs | Completed
Sales Force Automation | tender_template | Completed
Sales Force Automation | tax_master | Completed
Sales Force Automation | product_rate | Completed
Sales Force Automation | project_master | Completed
Sales Force Automation | product_group | Completed
Sales Force Automation | product_category | Completed
Sales Force Automation | product_brand | Completed
Sales Force Automation | edit_mail_settings | Completed
Sales Force Automation | opportunity_rate | Completed
Sales Force Automation | opportunity | Completed
Sales Force Automation | measure_unit | Completed
Sales Force Automation | mail_settings | Completed
Sales Force Automation | add_template | Completed
Sales Force Automation | customer_group | Completed
Sales Force Automation | add_project_master | Completed
Sales Force Automation | add_tax_master | Completed
Sales Force Automation | add_product_master | Completed
Sales Force Automation | add_product_group | Completed
Sales Force Automation | add_product_category | Completed
Sales Force Automation | add_opportunity | Completed
Sales Force Automation | add_measure_unit | Completed
Sales Force Automation | add_mail_settings | Completed
Sales Force Automation | add_customer_master | Completed
Sales Force Automation | add_customer_group | Completed
Sales Force Automation | add_product_brand | Completed
Sales Force Automation | add_opportunity_rate | Completed

## PMS-Work Schedule
PMS - Work Schedule
Year 2020
Work | 2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31 | 2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07 | 2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12
Purchase order QC | 2020-05-25: Varsha; 2020-05-31: Holiday; 2020-06-06: Holiday
Approval assignment QC | 2020-05-26: Divya
Approval hierarchy QC | 2020-05-27: Varsha
Approval set QC | 2020-05-27: Divya
Document workflow QC | 2020-05-29: Divya; 2020-05-30: Holiday
Note attachment design issue, Set menu icons for PMS pages | 2020-05-29: Varsha
Note in purchase order | 2020-05-29: Varsha
PO-Comment ,quick search,copy from PO(QC),status popup | 2020-06-02: Divya; 2020-06-08: Divya
Approval console | 2020-05-30: Varsha; 2020-06-01: Varsha
View active approval sets, comments , notes | 2020-06-09: Divya
request for additional details in approval console
Mail and dashboard alerts for orders and approval, CSV,PDF | 2020-06-11: Will consider later
Report | bar: 2020-06-11 to 2020-06-12
Make the changes in the GIT local folder with the changes that she made after the integration by varsha. Update the DB modifications to the to the DB that we provided from the production environment, from the DB which she is using in TVM. Need to contine the works from tuesday with the latest DB changes which is in the new DB which is updated and GIT folder application.

## Compzit-Design Work Schedule
Compzit - Redesign - Work Schedule
Module | Page | time axis 2020-05-25 to 2021-02-21
App Administration | add_business_unit | 2020-05-25: 5 days for the develoment, including the new option to print. The designer need to change the list pages of these and place search option at the botton of the labels in the header, place print icon in the right side of the pages.
App Administration | add_bank | bar: 2020-05-25 to 2020-05-30
App Administration | bank | bar: 2020-05-25 to 2020-05-30
App Administration | business_unit | bar: 2020-05-25 to 2020-05-30
App Administration | edit_organization | 2020-05-26: Review by the designers. Need to change, if anything wrong.Print button should be there in pages. Check consistancy. Change the file name as standard.; 2020-05-27: Management/Client Review; 2020-05-28: Changes, after the review
App Administration | add_premise | bar: 2020-05-26 to 2020-05-28
App Administration | add_premise_area | bar: 2020-05-26 to 2020-05-28
App Administration | add_corp_department | bar: 2020-05-26 to 2020-05-28
App Administration | add_city | bar: 2020-05-26 to 2020-05-28
App Administration | add_state | bar: 2020-05-26 to 2020-05-28
App Administration | add_time_slot | bar: 2020-05-26 to 2020-05-28
App Administration | add_complaint | bar: 2020-05-26 to 2020-05-28
App Administration | add_insurance | bar: 2020-05-26 to 2020-05-28
App Administration | insurance | bar: 2020-05-26 to 2020-05-28
App Administration | edit_password | bar: 2020-05-26 to 2020-05-28
App Administration | password | bar: 2020-05-26 to 2020-05-28
App Administration | add_corp_division | bar: 2020-05-26 to 2020-05-28
App Administration | add_workstation | bar: 2020-05-26 to 2020-05-28
App Administration | premise_area | bar: 2020-05-26 to 2020-05-28
App Administration | premise | bar: 2020-05-26 to 2020-05-28
App Administration | add_corp_partner | bar: 2020-05-26 to 2020-05-28
App Administration | add_country | bar: 2020-05-26 to 2020-05-28
App Administration | corp_division | bar: 2020-05-26 to 2020-05-28
App Administration | city | bar: 2020-05-26 to 2020-05-28
App Administration | corp_partner | bar: 2020-05-26 to 2020-05-28
App Administration | corp_department | bar: 2020-05-26 to 2020-05-28
App Administration | complaint | bar: 2020-05-26 to 2020-05-28
App Administration | workstation | bar: 2020-05-26 to 2020-05-28
App Administration | time_slot | bar: 2020-05-26 to 2020-05-28
App Administration | country | bar: 2020-05-26 to 2020-05-28
App Administration | state | bar: 2020-05-26 to 2020-05-28
Auto Workshop Management System | add_leave_typ | 2020-05-27: Designer review(If anything missing , change). Add print button. List search textboxes should be in bottom.; 2020-05-29: Management/Client Review
Auto Workshop Management System | add_trafic_viola_settlemnt | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | add_water_card | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | add_water_card_rechrg | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | add_vehicle | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | add_job | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | add_holiday_deatls | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | add_traffic_violation | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | water_card_rechrg | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | water_card | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | water_billing | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | vehicle_sts_mstr | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | vehicle_renwl_lst | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | vehicle_lst | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | vehicle_cls | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | vehicle_altmnt | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | trafic_violation | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | trafic_viola_settlemnt | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | time_sheet_rprt | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | leave_typ | bar: 2020-05-27; 2020-05-29
Auto Workshop Management System | job_schedule | bar: 2020-05-27
Auto Workshop Management System | insrnce_typ | bar: 2020-05-27
Auto Workshop Management System | holiday | bar: 2020-05-27
Auto Workshop Management System | fuel_typ | bar: 2020-05-27
Auto Workshop Management System | emply_off_duty | bar: 2020-05-27
Auto Workshop Management System | duty_roster_rprt | bar: 2020-05-27
Auto Workshop Management System | duty_roster | bar: 2020-05-27
Auto Workshop Management System | add_water_billing | bar: 2020-05-27
Auto Workshop Management System | add_vhcl_insre_renwl | bar: 2020-05-27
Auto Workshop Management System | add_vehicle_sts_mstr | bar: 2020-05-27
Auto Workshop Management System | add_vehicle_cls | bar: 2020-05-27
Auto Workshop Management System | add_vehicle_asgn | bar: 2020-05-27
Auto Workshop Management System | add_job_schedule | bar: 2020-05-27
Auto Workshop Management System | add_insrnce_typ | bar: 2020-05-27
Auto Workshop Management System | add_fuel_typ | bar: 2020-05-27
Auto Workshop Management System | job | bar: 2020-05-27
Gurantee Management System | policy | bar: 2020-05-27
Gurantee Management System | prjct_wse_grnty_rpt | bar: 2020-05-27
Gurantee Management System | notfiction_tmplte | bar: 2020-05-27
Gurantee Management System | supplr_rpt_wys | bar: 2020-05-27
Gurantee Management System | supplr_rpt_opn_status | bar: 2020-05-27
Gurantee Management System | supplr_rpt_expry_3mnth | bar: 2020-05-27
Gurantee Management System | rqst_4_guarant | bar: 2020-05-27
Gurantee Management System | supplr_rpt_crntly_rning | bar: 2020-05-27
Gurantee Management System | mail_trckng_rpt | bar: 2020-05-27
Gurantee Management System | job_catgry | bar: 2020-05-27
Gurantee Management System | insrnce_rpt_projct_wys | bar: 2020-05-27
Gurantee Management System | insrnce_rpt_typ_bsd | bar: 2020-05-27
Gurantee Management System | insrnce_rpt_opn_status | bar: 2020-05-27
Gurantee Management System | insrnce_rpt_expired | bar: 2020-05-27
Gurantee Management System | insrnce_rpt_expry_rnge | bar: 2020-05-27
Gurantee Management System | insrnce_rpt_expry_3mnth | bar: 2020-05-27
Gurantee Management System | cntrct | bar: 2020-05-27
Gurantee Management System | custmr_rpt_crntly_rning | bar: 2020-05-27
Gurantee Management System | custmr_rpt_expired | bar: 2020-05-27
Gurantee Management System | custmr_rpt_expry_3mnth | bar: 2020-05-27
Gurantee Management System | custmr_rpt_grnty | bar: 2020-05-27
Gurantee Management System | custmr_rpt_opn_status | bar: 2020-05-27
Gurantee Management System | grnty_expry_rng_rpt | bar: 2020-05-27
Gurantee Management System | grnty_mod_wis_rpt | bar: 2020-05-27
Gurantee Management System | guarnty_catgry | 2020-05-28: Designer review(If anything missing , change). Add print button. List search textboxes should be in bottom.
Gurantee Management System | add_rqst_4_guarant | bar: 2020-05-28
Gurantee Management System | add_cntrct | bar: 2020-05-28
Gurantee Management System | add_guarnty_catgry | bar: 2020-05-28
Gurantee Management System | add_policy | bar: 2020-05-28
Gurantee Management System | add_notfiction_tmplte | bar: 2020-05-28
Gurantee Management System | add_job_catgry | bar: 2020-05-28
Gurantee Management System | add_cntrct_catgry | bar: 2020-05-28
Gurantee Management System | insrnce_typ | bar: 2020-05-28
Gurantee Management System | insrnce_rpt_crntly_rning | bar: 2020-05-28
Gurantee Management System | add_insrnce_typ | bar: 2020-05-28
Gurantee Management System | cntrct_catgry | bar: 2020-05-28
Gurantee Management System | exprd_bnk_grnty_rpt | bar: 2020-05-28
Human Capital Management | attendace_report | bar: 2020-05-28
Human Capital Management | add_emply_job_assign | bar: 2020-05-28
Human Capital Management | emply_page_new | bar: 2020-05-28
Human Capital Management | rpt_emply_adtn_dedctn | bar: 2020-05-28
Human Capital Management | mntly_slry_stmnt | bar: 2020-05-28
Human Capital Management | leave_aplction_sts_rtp | bar: 2020-05-28
Human Capital Management | add_leave_aplction_sts_rtp | bar: 2020-05-28
Human Capital Management | app_settings | bar: 2020-05-28
Human Capital Management | bulk_labr | bar: 2020-05-28
Human Capital Management | graph_test | bar: 2020-05-28
Human Capital Management | immigrtion_asgnmt | bar: 2020-05-28
Human Capital Management | add_immigrtion_round | bar: 2020-05-28
Human Capital Management | immigrtion_rounds | bar: 2020-05-28
Human Capital Management | joining_intmtion_edit | bar: 2020-05-28
Human Capital Management | joining_intmtion | bar: 2020-05-28
Human Capital Management | interview_process_edit | bar: 2020-05-28
Human Capital Management | intrvw_procss | bar: 2020-05-28
Human Capital Management | intrvw_panel_edit | 2020-05-29: Review by the designers. Need to change, if anything wrong.Print button should be there in pages. Check consistancy. Change the file name as standard.
Human Capital Management | appointmnt_lttr | bar: 2020-05-29
Human Capital Management | add_appointmnt_lttr | bar: 2020-05-29
Human Capital Management | shrtlist_cndidate_edit | bar: 2020-05-29
Human Capital Management | add_candidte_selection | bar: 2020-05-29
Human Capital Management | candidat_selctn | bar: 2020-05-29
Human Capital Management | add_interview_cat | bar: 2020-05-29
Human Capital Management | require_allocation | bar: 2020-05-29
Human Capital Management | job_notification | bar: 2020-05-29
Human Capital Management | job_notification_click | bar: 2020-05-29
Human Capital Management | slry_entry_process | bar: 2020-05-29
Human Capital Management | payroll_strctr | bar: 2020-05-29
Human Capital Management | add_job_descrptn | bar: 2020-05-29
Human Capital Management | job_role | bar: 2020-05-29
Human Capital Management | add_employee | bar: 2020-05-29
Human Capital Management | add_manpwr_reqmnt | bar: 2020-05-29
Human Capital Management | manpowr_reqrmnt | bar: 2020-05-29
Human Capital Management | add_license_type | bar: 2020-05-29
Human Capital Management | add_acco_type | bar: 2020-05-29
Human Capital Management | accomodation_type | bar: 2020-05-29
Human Capital Management | add_eply_role_aloction | bar: 2020-05-29
Human Capital Management | add_designation | bar: 2020-05-29
Human Capital Management | designation_mstr | bar: 2020-05-29
Human Capital Management | emply_attendnce_port | bar: 2020-05-29
Human Capital Management | add_emply_bulk | bar: 2020-05-29
Human Capital Management | add_emply_single | bar: 2020-05-29
Human Capital Management | employee_transfer | bar: 2020-05-29
Human Capital Management | add_indvdual_leave_typ | bar: 2020-05-29
Human Capital Management | end_of_srvce_settlmnt | bar: 2020-05-29
Human Capital Management | emply_rol_allow | bar: 2020-05-29
Human Capital Management | emply_registratn | bar: 2020-05-29
Human Capital Management | emply_mess_exceptn | bar: 2020-05-29
Human Capital Management | emply_deductn | bar: 2020-05-29
Human Capital Management | emply_cndct_incidnt | bar: 2020-05-29
Human Capital Management | employee_condct | bar: 2020-05-29
Human Capital Management | emp_dtl_rpt | bar: 2020-05-29
Human Capital Management | daily_attendance | bar: 2020-05-29
Human Capital Management | duty_rejoin | bar: 2020-05-29
Human Capital Management | consultancy | bar: 2020-05-29
Human Capital Management | add_certificate_bundle | bar: 2020-05-29
Human Capital Management | arrival_confrmtion | bar: 2020-05-29
Human Capital Management | add_worker | bar: 2020-05-29
Human Capital Management | add_staff | bar: 2020-05-29
Human Capital Management | add_job_role | bar: 2020-05-29
Human Capital Management | add_performance_template | bar: 2020-05-29
Human Capital Management | add_performance_form | bar: 2020-05-29
Human Capital Management | add_pay_grade | bar: 2020-05-29
Human Capital Management | add_notice_period | bar: 2020-05-29
Human Capital Management | add_leave_type | bar: 2020-05-29
Human Capital Management | add_exprnce_crtfcte_gen | bar: 2020-05-29
Human Capital Management | add_consltncy | bar: 2020-05-29
Human Capital Management | add_accommodation | bar: 2020-05-29
Human Capital Management | accomodation | bar: 2020-05-29
Human Capital Management | welfare_service_transction | bar: 2020-05-29
Human Capital Management | add_welfare_service_transaction | bar: 2020-05-29
Human Capital Management | add_welfare_service_category | bar: 2020-05-29
Human Capital Management | welfare_service_category | bar: 2020-05-29
Human Capital Management | add_welfare_service | bar: 2020-05-29
Human Capital Management | welfare_service | bar: 2020-05-29
Human Capital Management | add_visa_quota | bar: 2020-05-29
Human Capital Management | visa_quota
Human Capital Management | add_team_hier
Human Capital Management | team_hier
Human Capital Management | add_salary_certificate
Human Capital Management | salary_certificate
Human Capital Management | leave_approval
Human Capital Management | ref_leave_approval
Human Capital Management | performance_templ
Human Capital Management | performance_form
Human Capital Management | add_paymnt_closng_process
Human Capital Management | payment_closing
Human Capital Management | pay_grade
Human Capital Management | add_overtime_category
Human Capital Management | overtime_category
Human Capital Management | notice_period
Human Capital Management | monthly_attendance
Human Capital Management | add_monthly_attendance
Human Capital Management | add_mess_bill
Human Capital Management | mess_bill_cal
Human Capital Management | licence_type
Human Capital Management | leave_type
Human Capital Management | add_leave_settlemnt
Human Capital Management | leave_settlement
Human Capital Management | add_leave_reqst
Human Capital Management | leave_request
Human Capital Management | add_leave_allocation
Human Capital Management | leave_allocation
Human Capital Management | joining_worker
Human Capital Management | job_descrptn
Human Capital Management | intrvw_templte
Human Capital Management | intrvw_panel
Human Capital Management | intrvw_catgry
Human Capital Management | generate_wps
Human Capital Management | add_generate_wps
Human Capital Management | add_exit_intrvw_qstn
Human Capital Management | ext_intrvw_question
Human Capital Management | exprnce_crtfcte_genrtion
Human Capital Management | exit_intrview_process_click
Human Capital Management | exit_intrvw_process
Human Capital Management | add_end_of_srvce_settlmnt
Human Capital Management | add_emplye_cndct_catgry
Human Capital Management | emplye_cndct_catgry
Human Capital Management | emply_sponsor
Human Capital Management | add_emply_sponsor
Human Capital Management | add_emply_mess_exceptn
Human Capital Management | add_emply_deductn
Human Capital Management | add_emply_cndct_incidnt
Human Capital Management | add_daily_attendance_sheet
Human Capital Management | add_clearance_form_worker
Human Capital Management | clearance_form_workr
Human Capital Management | add_certfcate_vlidtion
Human Capital Management | certfcate_vlidtion
Human Capital Management | certfcate_bundl_temp
Human Capital Management | candidat_short
Human Capital Management | add_adictn_dedctn_nrml
Human Capital Management | adictn_dedctn
Human Capital Management | add_monthly_salary_process
Human Capital Management | add_exit_process
Human Capital Management | add_adictn_dedctn
Human Capital Management | add_accomdtion_catgry
Human Capital Management | visa_profession
Human Capital Management | rpt_visa_quota_status
Human Capital Management | rpt_visa_bundle
Human Capital Management | rpt_payroll_process
Human Capital Management | rpt_onbrdng_job_asgnmnt
Human Capital Management | rpt_onboarding_status
Human Capital Management | rpt_mess_calculation
Human Capital Management | rpt_manpwr_prcess_dtl
Human Capital Management | rpt_manpwr_job_asgnment
Human Capital Management | rpt_man_powr_rqrmnt_sts
Human Capital Management | rpt_leave_mngmnt
Human Capital Management | rpt_leave_application
Human Capital Management | rpt_job_ofr_status
Human Capital Management | rpt_job_cst_smmry
Human Capital Management | rpt_intrvw_evaltion
Human Capital Management | rpt_intrview_summry
Human Capital Management | rpt_imigrtion_task
Human Capital Management | rpt_expry_notification
Human Capital Management | rpt_emply_recruit
Human Capital Management | rpt_emply_deduction_dtl
Human Capital Management | rpt_emp_dtl
Human Capital Management | rpt_attendance
Human Capital Management | rpt_accomodation
Human Capital Management | resignation_apprvl
Human Capital Management | resignation
Human Capital Management | performance_evaluation
Human Capital Management | payslip_generation
Human Capital Management | passport_hnd_ovr_sts
Human Capital Management | opening_leave_alloctn
Human Capital Management | onboardng_task
Human Capital Management | onboardng_procss
Human Capital Management | notice_period_alloction
Human Capital Management | mntly_slry_stmnt_wrkr
Human Capital Management | leave_partial
Human Capital Management | leave_facility_assgnmnt
Human Capital Management | joining_staff
Human Capital Management | job_delegation
Human Capital Management | import_csv
Human Capital Management | immigrtion_task
Human Capital Management | exit_procedure
Human Capital Management | exit_partl_process
Human Capital Management | emply_exit_process
Human Capital Management | clearance_form_apprvl
Human Capital Management | candidate_login_page
Human Capital Management | candidate_id_generate
Human Capital Management | accomdtion_catgry
Procurement Management Solution | prchse_ordr
Procurement Management Solution | add_purchase
Procurement Management Solution | ware_house
Procurement Management Solution | active_apprvl
Procurement Management Solution | add_apprvl_console
Procurement Management Solution | add_replace_apprvr
Procurement Management Solution | add_dcmnt_wrkflow
Procurement Management Solution | dcmt_work
Procurement Management Solution | add_apprvl_assmnt
Procurement Management Solution | apprvl_assmnt
Procurement Management Solution | approvl-set_list
Procurement Management Solution | add_apprvl_set
Procurement Management Solution | aprved_hie_tmp
Procurement Management Solution | add_aprved_hie_tmp
Procurement Management Solution | vendor
Procurement Management Solution | add_vendor
Procurement Management Solution | add_warehouse
Procurement Management Solution | approvl-set_dcmt
Procurement Management Solution | add_charge_heads
Procurement Management Solution | charge_heads
Sales Force Automation | product_master
Sales Force Automation | customer_master
Sales Force Automation | rpt_custom_se
Sales Force Automation | rpt_active_opp
Sales Force Automation | rpt_daily_se
Sales Force Automation | rpt_daily_dm
Sales Force Automation | rpt_custom_dm
Sales Force Automation | rpt_booking_se
Sales Force Automation | rpt_booking_dm
Sales Force Automation | rpt_opportunity
Sales Force Automation | ref_opportunity
Sales Force Automation | rpt_itemlist
Sales Force Automation | template
Sales Force Automation | standard_template
Sales Force Automation | project_template
Sales Force Automation | rpt_qs
Sales Force Automation | tender_template
Sales Force Automation | tax_master
Sales Force Automation | product_rate
Sales Force Automation | project_master
Sales Force Automation | product_group
Sales Force Automation | product_category
Sales Force Automation | product_brand
Sales Force Automation | edit_mail_settings
Sales Force Automation | opportunity_rate
Sales Force Automation | opportunity
Sales Force Automation | measure_unit
Sales Force Automation | mail_settings
Sales Force Automation | add_template
Sales Force Automation | customer_group
Sales Force Automation | add_project_master
Sales Force Automation | add_tax_master
Sales Force Automation | add_product_master
Sales Force Automation | add_product_group
Sales Force Automation | add_product_category
Sales Force Automation | add_opportunity
Sales Force Automation | add_measure_unit
Sales Force Automation | add_mail_settings
Sales Force Automation | add_customer_master
Sales Force Automation | add_customer_group
Sales Force Automation | add_product_brand
Sales Force Automation | add_opportunity_rate